## Sheet1
Weeks | tasks
2020-10-01 | set up GitHub and Azure Cli
2020-10-08 | create project scaffolding
2020-10-15 | local test
2020-10-22 | configure github acctions
2020-10-29 | verify remote test
2020-11-05 | CD using azure
2020-11-12 | deploy app
2020-11-19 | test Deployment on Azure
2020-11-26 | make predictions
2020-12-03 | inspect log
2020-12-10 | QA
2020-12-17
| Goals | Order Prioritized Features | time in week | Proposed Difficult(1-3) | Project Management Guidelines
| set up GitHub and Azure Cli | 1 | 1 | 1 | Demo every mondy
| test CICD | 2 | 4 | 1 | Weekly planning after demo
| Deploy on Azure | 3 | 4 | 3 | Tickets represent 4 hours block work
| make predictions | 4 | 2 | 2